## UPS Gate Review
HIGH CONFIDENCE CONCRETE PLACEMENT READINESS REVIEW CHECKLIST
PRE-PLACEMENT TECHNICAL SUBMITTALS PER 03 3021 (using pre-approved mix design)
Submittal # | Spec Reference | Description | Status Code | Comments | Complete
1 | 03 3021 | Subcontractor Quality Assurance (QA) Program including all subtier subcontracts
1.5.A.1.a
2 | 03 3021 | Commercial Grade Dedication Plan compliant with ASME NQA-1 for concrete, concrete constituents and reinforcing steel
1.5.A.1.b
3 | 03 3021 | Verification of Inspection and Test Plan (VIT Plan)
1.5.A.1.c
4 | 03 3021 | Documentation required by VIT Plan (logs and results of tests and inspections performed)
1.5.A.1.d
5 | 03 3021 | Documentation that testing agencies have been accepted by the LANL Building Official (LBO) and EOR.
1.5.A.1.e
6 | 03 3021 | Documentation that testing agencies have a quality program complying with ASME NQA-1-2008 (with the NQA-1a-2009 addenda).
1.5.A.1.f
7 | 03 3021 | Quality Assurance/Quality Control Program of the concrete supplier
1.5.A.1.g
8 | 03 3021 | Drawings: Installation of reshoring and backshoring
1.5.A.2.a
9 | 03 3021 | Procedures: Installation of reshoring and backshoring
1.5.A.2.a
10 | 03 3021 | Data on formwork release agent or formwork liners
1.5.A.2.b
11 | 03 3021 | Design calculations: Formwork
1.5.A.2.c
12 | 03 3021 | Design calculations: Shoring
1.5.A.2.c
13 | 03 3021 | Design calculation: Reshoring
1.5.A.2.c
14 | 03 3021 | Drawings: Formwork
1.5.A.2.c
15 | 03 3021 | Drawings: Shoring
1.5.A.2.c
16 | 03 3021 | Drawings: Reshoring
1.5.A.2.c
17 | 03 3021 | Data Sheet: Form Ties
1.5.A.2.d
18 | 03 3021 | Data Sheet: Sealer
1.5.A.2.e
19 | 03 3021 | Data Sheet: Filler
1.5.A.2.e
20 | 03 3021 | Confirmation of receipt of sample of expansion joint materials (sealer and filler)
1.5.A.2.e
21 | 03 3021 | Data Sheet: Form-facing materials
1.5.A.2.f
22 | 03 3021 | Rebar Certified Material Test Report traceable to the heat# on shipping tags, and tags themselves
1.5.A.3.a
23 | 03 3021 | Rebar Shop Drawings
1.5.A.3.b
24 | 03 3021 | Certified Material Test Report: Other Construction Materials (pre-stress strands, Form Savers, cadwelds, etc…)
1.5.A.3.c
25 | 03 3021 | ICC ESR Reports for Mechanical Splices
1.5.A.3.c
26 | 03 3021 | Certified Material Test Report for steel embedments in concrete
1.5.A.3.d
27 | 03 3021 | Plan identifying location, duration, and magnitude of construction loads exceeding deisgn loads or prior to achieving 100% strength (if applicable)
1.5.A.5.f
28 | 03 3021 | Subcontractor Cold Weather Plan
1.5.A.5.g
29 | 03 3021 | Subcontractor Cold Weather Protection Activities
1.5.A.5.g
30 | 03 3021 | Subcontractor Hot Weather Plan
1.5.A.5.h
31 | 03 3021 | Description of conveying equipment
1.5.A.5.i
32 | 03 3021 | Hazardous/Inclement/Wet Weather Placement Protection Plan
1.5.A.5.j
33 | 03 3021 | Method of measuring concrete surface temperature changes
1.5.A.5.k
34 | 03 3021 | Method of removal of stains, rust, efflorescence, and surface deposits
1.5.A.5.l
35 | 03 3021 | Qualifications of finishing Subcontractor and flatwork finishers
1.5.A.5.m
LOGISTICS
Item | Focus | Description | Controls/Plans in Place | Comments | Complete
1 | People | Adequate resources to perform work
2 |  | Adequate pre-approved resources to perform testing
3 |  | Pre-pour checklist complete @ 1 week
4 |  | EOR Pre-pour inspections complete @ 1 day
5 |  | FE/QA Support scheduled and available
6 | Equipment | Back-up pump truck available
7 |  | Accessibility to work area confirmed/Traffic Plan
8 |  | Adequate number of concrete trucks scheduled
9 |  | Washout bins available, lined, leak tested
10 |  | Secondary containment in place for washout bins
11 |  | Sufficient number of vibrators available (back ups), finishing tools
12 | Schedule | Start time coordinated to allow for traffic/ delays
13 |  | Weather contingencies in place
14 |  | Confirm start/end of day's placement
Security
15 | Badges | Visitor Badges Needed - Subcontractor
Visitor Badges Needed - LATM
Pump Truck Operator(s)
16 | Activity Security Plan (ASP) | Generated, up to date, and approved?
Communicated to Proforce?
Compa Escorts Scheduled?
17 |  | Security plan in place for Pajarito Cooridor
18 | Safety/Work Plan | IWDs complete and approved
19 |  | Work Plans complete, approved, personnel briefed
20 |  | Adequate lighting for early / late activities
21 |  | Access/ egress for visitors away from hazards
22 |  | Availability of ladders where needed
23 |  | Secure worker badges while pouring
24 |  | Generators & adequate length power cords
25 |  | Trash containers for housekeeping
26 |  | Water available for masons/breaks
| Inspection |  |  | Subcontractor QC Check
27 | Rebar | Footings |  | LANL FE Check
EOR Check
28 |  | Thickened Slab Area |  | Subcontractor QC Check
LANL FE Check
EOR Check
29 | Piping/Embeds | Floor Drains and Trap Primers
Drains
30 | Formwork | Anchor Bolt Template/Layout
Sloping of Slab
Forms for recessed areas
Mud Mat Frames
31 | Inspection Checklist | Review LANL FE Checklist
Review Subcontractor Workplan Checklists
32 | Weather Conditions | Review forecast conditions for placement dates
33 | Post Concrete | Curing Compound/Curing Mats
Protect from wind/rain
|  | Cylinder storage area/protection/quantity |  | Coolers must be properly labeled
Confirm form removal requirements, procedures, and timing
34 | Notifications | Communicate site access restrictions
Develop visitor access plan
Coordinate plan with Facility Operations

## Sheet1
Exhibit I No. | Description | Spec Reference | Comments | Status Code | Complete
5.0148 | Subcontractor Quality Assurance (QA) Program including all subtier subcontracts | 03 3001.01
1.5.A
5.0149 | Commercial Grade Dedication Plan compliant with ASME NQA-1 for concrete, concrete constituents and reinforcing steel | 03 3001.01
1.5.A
5.015 | Verification of Inspection and Test Plan (VIT Plan) | 03 3001.01
1.5.A
5.0151 | Documentation required by VIT Plan (logs and results of tests and inspections performed) | 03 3001.01
1.5.A
5.0152 | Documentation that testing agencies have been accepted by the Contractor | 03 3001.01
1.5.A
5.0153 | Documentation that testing agencies have been accepted by the LANL Building Official (LBO) and are NQA-1 compliant. | 03 3001.01
1.5.A
5.0154 | Quality Assurance/Quality Control Program of the concrete supplier | 03 3001.01
1.5.A
5.0155 | Test and Inspection results from the subcontractor's testing agency that pertain to the Work | 03 3001.01
1.5.A
5.0156 | Drawings: Installation of reshoring and backshoring | 03 3001.01
1.5.A
5.0157 | Procedures: Installation of reshoring and backshoring | 03 3001.01
1.5.A
5.0158 | Data on formwork release agent or formwork liners | 03 3001.01
1.5.A
5.0159 | Design calculations: Formwork | 03 3001.01
1.5.A
5.016 | Design calculations: Shoring | 03 3001.01
1.5.A
5.0161 | Design calculation: Reshoring | 03 3001.01
1.5.A
5.0162 | Drawings: Formwork | 03 3001.01
1.5.A
5.0163 | Drawings: Shoring | 03 3001.01
1.5.A
5.0164 | Drawings: Reshoring | 03 3001.01
1.5.A
5.0165 | Data Sheet: Form Ties | 03 3001.01
1.5A
5.0166 | Data Sheet: Sealer | 03 3001.01
1.5.A
5.0167 | Data Sheet: Filler | 03 3001.01
1.5.A
5.0168 | Confirmation of receipt of sample of expansion joint materials (sealer and filler) | 03 3001.01
1.5.A
5.0169 | Data Sheet: Form-facing materials | 03 3001.01
1.5.A
5.017 | Certified Material Test Report: Rebar | 03 3001.01
1.5.A
5.0171 | Shop Drawings | 03 3001.01
1.5.A
5.0172 | Certified Material Test Report: Reinforcing Construction Materials | 03 3001.01
1.5.A
5.0173 | Certified Material Test Report: Other Construction Materials | 03 3001.01
1.5.A
5.0174 | Certified Material Test Report: Steel Embedment in Concrete | 03 3001.01
1.5.A
5.0175 | Certified Material Test Report: Aggregates | 03 3001.01
1.5.A.4
5.0176 | Certified Material Test Report: Cement | 03 3001.01
1.5.A.4
5.0177 | Certified Material Test Report: Other Cementitious Materials | 03 3001.01
1.5.A.4
5.0178 | Certified Material Test Report: Water Source | 03 3001.01
1.5.A.4
5.0179 | Test Report: Aggregates | 03 3001.01
1.5.A.4
5.018 | Test Report: Cement | 03 3001.01
1.5.A.4
5.0181 | Test Report: Other Cementitious Materials | 03 3001.01
1.5.A.4
5.0182 | Test Report: Water Source | 03 3001.01
1.5.A.4
5.0183 | Product Data: Aggregates | 03 3001.01
1.5.A.4
5.0184 | Product Data: Cement | 03 3001.01
1.5.A.4
5.0185 | Product Data: Other Cementitious Materials | 03 3001.01
1.5.A.4
5.0186 | Product Data: Water Source | 03 3001.01
1.5.A.4
5.0187 | Product Data: Admixtures | 03 3001.01
1.5.A.4
5.0188 | Product Data: Materials for Curing/Repair Materials | 03 3001.01
1.5.A.4
5.0189 | Product Data: Other Manufactured Products | 03 3001.01
1.5.A.4
5.019 | Methodology and test data used to establish mixture proportions | 03 3001.01
1.5.A.4
5.0191 | Mix proportions and characteristics | 03 3001.01
1.5.A.4
5.0192 | Information on types, classes, producers' names, and plant locations for cementitious materials | 03 3001.01
1.5.A
5.0193 | Documentation indicating compliance of the mix design with the specified requirements for sulfate resistance | 03 3001.01
1.5.A
5.0194 | Documentation verifying compliance with specified requirements for freezing and thawing exposure. | 03 3001.01
1.5
5.0195 | Concrete placement records | 03 3001.01
1.5
5.0196 | Concrete cylinder test reports and charts | 03 3001.01
1.5
5.0197 | Reports for construction removal of forms and reshoring | 03 3001.01
1.5
5.0198 | Construction loadings on completed floors, members, or walls | 03 3001.01
1.5
5.0199 | Subcontractor Cold Weather Plan | 03 3001.01
1.5
5.02 | Subcontractor Cold Weather Protection Activities | 03 3001.01
1.5
5.0201 | Subcontractor Hot Weather Plan | 03 3001.01
1.5
5.0202 | Hazardous/Inclement Weather Placement Protection Plan | 03 3001.01
5.0203 | Description of conveying equipment | 03 3001.01
1.5
5.0204 | Method of measuring concrete surface temperature changes | 03 3001.01
1.5
5.0205 | Method of removal of stains, rust, efflorescence, and surface deposits | 03 3001.01
1.5
5.0206 | Qualifications of Subcontractor and flatwork finishers | 03 3001.01
1.5
5.0207 | Description of pre-placement activities | 03 3001.01
1.5
5.0208 | Description of Wet Weather Protection Activities | 03 3001.01
1.5
5.0209 | Batch Tickets | 03 3001.01
1.5
5.021 | Documents used to establish compliance with standards and regulations that pertain to performance of the Work | 03 3001.01
1.5
5.0211 | Complete record of tests of materials and concrete | 03 3001.01
2.1
5.0212 | ICC Evaluation Reports: Form Savers | 03 3001.01
2.3
5.0213 | ICC Evaluation Reports: Cadwelds | 03 3001.01
2.3
5.0214 | ICC Evaluation Reports: Mechanical Splices | 03 3001.01
2.3
5.0215 | ICC Evaluation Reports: Other Construction Materials | 03 3001.01
2.3
5.0216 | Certified Material Test Reports: Filler Material | 03 3001.01
2.3
5.0217 | Certified Mill Test Report: Cement | 03 3001.01
2.4
5.0218 | Petrographic Examination Report & Associated Test Reports | 03 3001.01
2.4
5.0219 | Infrared spectrum trace of the conformance test sample of air-entraining and water-reducing admixture. | 03 3001.01
2.5
5.022 | Record of concrete temperatures and of protection given to concrete during placement and curing | 03 3001.01
3.5
5.0221 | Evidence that verifies that increased temperatures do not cause deterioration of the concrete with or in the absence of applied loads | 03 3001.01
3.1